## Slide 1: MITG / DMID Quarterly Program Review — Q3 FY26
• Prepared for program leadership and the portfolio review board
• Covers MITG task order, DMID delivery order, modifications pipeline, obligations posture, compliance, staffing, and Q1 recompete readiness
• FICTIONAL training sample — slides are intentionally overcrowded so you can practice trimming with Copilot

## Slide 2: Executive Summary
• Overall status GREEN trending YELLOW on MITG due to open Mod #14 and the compliance scope gap
• Near-term pressure point: OMB data call due Friday — Northwind portion still outstanding
• Audit kickoff at risk of a 1-2 week slip if the scope revision runs long
• Bridge extension filed so the MITG PoP does not lapse 9/30
• DMID recompete planning underway; Mod #14 precedent risk being tracked
• Three active contracts within ceiling; Tailspin fully invoiced and closing
• Staffing: one analyst cleared, one on interim pending final clearance
• No leadership decision required this week beyond awareness of the data-call risk

## Slide 3: MITG Task Order Status
• Contract MITG-2023-001, Northwind Solutions, T&M, ceiling $2.45M
• Obligated $2.18M (89%), invoiced $1.64M to date, remaining $0.54M
• Mod #14 adds 2 analysts, 60-day extension, $163K (over-$10K gate cleared by Contracts)
• Compliance review in progress, expected to clear Monday with a phased-start condition
• Risk: nearing ceiling depending on the option; a funding action may be needed if scope grows
• Performance on schedule; deliverables 4 and 5 accepted last period

## Slide 4: DMID Delivery Order Status
• Contract DMID-2022-014, Contoso Federal, FFP, ceiling $1.875M, fully obligated
• Invoiced $1.50M, remaining $0.37M, PoP ends 3/31/2027
• Recompete planning underway — sources-sought posted, six responses, draft PWS ~80%
• Risk: Mod #14 on MITG could set a precedent we do not want to carry into the recompete
• Tailspin DMID-2023-021 fully invoiced and closing out 6/30

## Slide 5: Modifications Pipeline
• Mod #12 (pricing-only) closed, 2-day compliance turn
• Mod #13 (admin) closed
• Mod #14 (scope + PoP, $163K) in Compliance, clears Monday
• Mod #15 (scope, TBD) at intake
• Process: COR intake, Finance budget, >$10K Contracts approval, Compliance by complexity, recommendation to COR
• Standard mods target 2 weeks; complex 3 weeks

## Slide 6: Budget & Obligations
• MITG obligated ~89% of the $2.45M ceiling; Mod #14 adds $163K — monitor against ceiling
• DMID fully obligated; $0.37M remaining to invoice through 3/31/2027
• Fabrikam (MITG-2024-009) ~62% obligated; on track
• Monthly actuals tracking within +/-18% of plan across active contracts
• No anti-deficiency risk identified this period

## Slide 7: Compliance & Audit
• Audit scope gap identified: third-party vendor assessment not included
• Scope revision adds ~1 week; scope call held with Legal/Finance/Audit
• Risk: audit kickoff slips 1-2 weeks if revision runs long
• Mod #14 flagged complex (scope + timeline) — insurance and rate-table checks in progress
• No open findings from the prior period

## Slide 8: Staffing & Clearances
• Northwind adding 2 analysts under Mod #14
• Analyst 1 cleared; Analyst 2 on interim, final expected ~2 weeks
• Phased start: cleared analyst begins on award; second on final clearance
• Controlled data set access gated on final clearance
• COR coverage: Chen (MITG, MITG-2025), Patel (Fabrikam, Tailspin)

## Slide 9: Risks & Issues
• OMB data call: Northwind portion outstanding — deadline risk for Friday
• Compliance scope revision duration uncertain (audit timeline impact)
• Second analyst clearance timing (resource ramp impact)
• Recompete precedent risk from Mod #14
• Mitigations in place for each; none require board action except the data-call escalation

## Slide 10: Timeline / Key Dates
• Wednesday EOD: Northwind data-call portion needed or we escalate further
• Thursday COB: Finance reconciliation complete for the data call
• Friday 3:00: OMB data call response submitted
• Monday: expected Mod #14 compliance clearance
• 9/30: MITG PoP (bridge extension filed); Q1 FY27: DMID recompete solicitation target

## Slide 11: Asks of Leadership
• Awareness of the OMB data-call deadline risk and the Northwind escalation
• Note the audit-kickoff slip risk and the mitigation
• Awareness of the recompete precedent consideration on Mod #14
• No funding action requested this week

## Slide 12: Appendix — Contract Detail (raw)
• See Budget_Tracker.xlsx for line-item ceilings, obligations, invoiced, and remaining
• Mods Log maintained separately
• All figures fictional and for training only