MITG / DMID PROGRAM — Bi-Weekly Status  (DRAFT)

period: 6/1-6/12    prepared by S. Chen    distribution: program leads, COR team, finance

Summary - Overall GREEN, trending yellow on the MITG task order due to the open Mod #14 and the compliance audit scope gap. DMID recompete planning is underway. The near-term pressure point is the OMB data call due Friday - Northwind has not returned their portion yet, and if it slips past Wednesday we are at risk on the deadline.

ACCOMPLISHMENTS THIS PERIOD

Closed out Mod #12 (pricing-only, 2-day compliance turn)

Northwind Mod #14 cost analysis complete - $163K / 60-day option recommended

Filed a no-cost bridge extension so the MITG PoP does not lapse Sept 30

Posted the sources-sought notice for the DMID recompete (six responses)

IN PROGRESS / NEXT PERIOD

Mod #14 through Compliance (Hung) - expected to clear Monday, phased analyst start due to clearance

Compliance audit scope revision to add third-party vendor assessment (~1 week)

OMB data call response - due Friday; Fabrikam in, Northwind outstanding, Finance reconciling

DMID recompete draft PWS ~80% complete; industry day in ~3 weeks

RISKS

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Northwind late on the OMB data call | Miss the Friday deadline | Escalated to Northwind PM; Boris cc’d; no extension without sign-off |
| Compliance audit scope revision runs long | Audit kickoff slips 1-2 wks | Scope call held; revising in parallel, back to Hung Friday |
| Second analyst clearance delay (Mod #14) | Resource ramp delayed | Phased start; cleared analyst begins on award |
| DMID draft PWS slips | RFP date pushes in Q1 | Lock PWS scope this month; Legal set-aside call early |

Open items / decisions needed: confirm phased-start condition with Northwind; document the 60-vs-90-day Mod #14 rationale in the file for the recompete; Legal determination on the small-business set-aside.

notes: numbers rough, finance to confirm. -SC