# Q3 Budget Review & Compliance Update

Prepared for: Program Leadership   |   Status: Draft for review   |   Fictional sample — training use only

# Overview

The Q3 budget allocation process is 85% complete, with final approval expected by end of week. In parallel, we have identified a critical gap in the compliance audit scope that requires immediate revision before the audit can begin.

# Budget Status by Department

Infrastructure ($45K) — APPROVED. Cloud migration project funded and underway.

Marketing ($60K) — PENDING LEGAL REVIEW. Campaign launch materials approved, but spend requires general counsel sign-off. Legal estimates 2-3 business days.

HR & Training ($20K) — APPROVED. Leadership training program investment cleared.

# Open Issues

1. Marketing Legal Review: Legal team processing the GC escalation. Expected decision Thursday EOD.

2. Compliance Audit Scope: Current scope does not include third-party vendor assessment. Scope revision needed before audit kickoff. Estimated 1 additional week to finalize the revised scope.

# Timeline

Today: HR budget approved

Tomorrow 10:00am: Compliance audit scope discussion (Legal, Finance, Audit)

Thursday EOD: Legal decision on marketing spend expected

Friday EOD: Final budget approval and revised compliance scope due

# Risks & Recommendations

Risk 1: If legal review extends beyond Thursday, budget approval slips to the following week.

Risk 2: Compliance scope revision may delay the audit start by 1-2 weeks.

Recommendation: Proceed with non-marketing spend approvals this week. Escalate the marketing legal review for faster turnaround. Hold the compliance scope discussion tomorrow to unblock the revision.